## FDP Form 7
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 3rd QUARTER, CY 2020
Province, City / Municipality: Ilocos Sur/ Bantay
Program or | Location | Total Cost | Date Started | Target | Project Status |  | No. of
Project |  |  |  | Completion | % of | Total Cost Incurred | Extensions, if | Remarks
|  |  |  | Date | Completion | to Date | any
Social Development
Rehabilitation of Gov't. centers and facilities | Bantay, I. Sur | 866027.4 |  |  | 0% | 0 |  | Bid on 8/18
Rehabilitation & Maint. of Historical/Cultural sites | -do- | 872344.2 |  |  |  | 0 |  | not yetstarted
Installation of Streetlights | Pob. Brgys. | 1259406 |  |  | 0% | 0 |  | not yet started
For COVID related expenses | Bantay, I. Sur | 809072.6 |  |  | 0% | 0 |  | ongoing
Construction of Public Restroom | Bantay Plaza | 800000 |  |  | 0% | 0 |  | not yet started
Purchase of Ambulance | RHU office | 2500000 |  |  | 0% | 0 |  | Bid on 9/30
|  | 7106850.2 |  |  |  | 0
Economic Development
Livestock Development (Provision for vaccines) | All barangays | 150000 |  |  | 0% | 0 |  | not yet started
Livelihood projects (Livestock dispersal) | All farming barangays | 1500000 |  |  | 0% | 0 |  | not yet started
Promotion & Development of organic fertilizer | 3 Farming baranagays | 150000 |  |  | 0% | 0 |  | not yet started
Provision of skills training on farming and livestock raising | 9 Farming barangays | 150000 |  |  | 0% | 0 |  | -do-
Enhancement of Agricultural Production | 9 Farming barangays | 150000 |  |  | 0% | 0 |  | -do-
|  | 2100000 |  |  |  | 0
Environmental Management
Construction of Residual Containment Area | Bantay Arcade | 200000 |  |  | 0% | 0 |  | -do-
Construction of Flood Control | Pus-pus-Sinabaan | 14000000 |  |  | 0% | 0 |  | -do-
|  | 14200000 |  |  |  | 0
We hereby certify that we have reviewed the contents and hereby attest to
the veracity and correctness of the data or information contained in this
document.
FLORDELIZA P. REBOROSO | [5 empty] | SAMUEL C. PARILLA
Municipal Budget Officer | [5 empty] | Municipal Mayor