## FDP Form 7
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 4th QUARTER, CY 2020
Province, City / Municipality: Ilocos Sur/ Bantay
Program or | Location | Total Cost | Date Started | Target | Project Status |  | No. of
Project |  |  |  | Completion | % of | Total Cost Incurred | Extensions, if | Remarks
|  |  |  | Date | Completion | to Date | any
Social Development
Rehabilitation of Gov't. centers and facilities | Bantay, I. Sur | 866027.4 | Sept. 7, 2020 | October 13,2020 | 100% | 792654.06 |  | completed
Installation of Streetlights | Pob. Brgys. | 1259406 |  |  | 0% | 0 |  | not yet started
For COVID related expenses | Bantay, I. Sur | 1681416.8 | October |  | 65% | 1100367.59 |  | ongoing
Construction of Public Restroom | Bantay Plaza | 800000 |  |  | 0% | 0 |  | not yet started
Purchase of Ambulance | RHU office | 2500000 |  | October | 100% | 2500000 |  | implemented
|  | 7106850.2 |  |  |  | 4393021.65
Economic Development
Livestock Development (Provision for vaccines) | All barangays | 150000 |  |  | 0% | 0 |  | not yet started
Livelihood projects (Livestock dispersal) | All farming barangays | 1500000 |  |  | 0% | 0 |  | not yet started
Promotion & Development of organic fertilizer | 3 Farming baranagays | 150000 |  |  | 0% | 0 |  | not yet started
Provision of skills training on farming and livestock raising | 9 Farming barangays | 150000 |  |  | 0% | 0 |  | not yet started
Enhancement of Agricultural Production | 9 Farming barangays | 150000 |  |  | 0% | 0 |  | not yet started
|  | 2100000 |  |  |  | 0
Environmental Management
Construction of Residual Containment Area | Bantay Arcade | 200000 |  |  | 0% | 0 |  | not yet started
Construction of Flood Control | Pus-pus-Sinabaan | 14000000 | Dec. 7, 2020 | June 5,2021 | 15% | 0 |  | on going
|  | 14200000 |  |  |  | 0
II. Continuing Appropriation
Social Development
Covid-related expenses |  | 1746230.6 | May | Dec |  | 1746230.6 |  | implemented
Environmental Management
Purchase of Lot for Sanitary Landfill |  | 3000000 | [5 empty] | not yet implemented
Procurement of Equipment for Sanitary Landfill |  | 1200000
Relocation of Talipapa |  | 483488.01
We hereby certify that we have reviewed the contents and hereby attest to
the veracity and correctness of the data or information contained in this
document.
FLORDELIZA P. REBOROSO | [5 empty] | SAMUEL C. PARILLA
Municipal Budget Officer | [5 empty] | Municipal Mayor