## FDP Form 7
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 2nd QUARTER, CY 2021
Province, City / Municipality: Ilocos Sur/ Bantay
Program or | Location | Total Cost | Date Started | Target | Project Status |  | No. of
Project |  |  |  | Completion | % of | Total Cost Incurred | Extensions, if | Remarks
|  |  |  | Date | Completion | to Date | any
I. Current Appropriation
Economic Development
Amortization of existing loans | Bantay, I. Sur | 8439866.52 | January | December | 50.32% | 4246736.42
|  | 8439866.52 |  |  |  | 4246736.42
Environment and Infrastracture Development
Desilting/Rechanelling of creek | Taleb | 4600000
Desilting/Rechanelling of creek | Sinabaan, Puspus, Aggay | 4400000
Desilting/Rechanelling of creek | Cabaroan | 1000000
Construction of Sanitary Landfill | Taleb.Bantay | 6646836.48 |  |  | 0% | 0
|  | 16646836.48 |  |  |  | 0
II. Continuing Appropriation
Social Development
Construction of Public Restroom | Town Plaza | 800000
Installation of Streetlights | Poblacion Brgys | 1259406
Covid-related expenses |  | 581049.21 | January | December | 96.44% | 560341.32 |  | on- going | i
|  | 2640455.21 |  |  |  | 560341.32
Economic Development
Livelihood Projects (Livestock Dispersal) |  | 1500000 | July | Dec
Livelihood Development (Vaccines) |  | 150000 | May | July
Promotion and Development of Organic Fertilizer |  | 150000 | July | Dec
Provision of skills traing on Farming & Livestock Raising |  | 150000 | July | Dec
Enhancement of Agricultural Production |  | 150000 | July | Dec
2100000
Environmental Management
Purchase of Lot for Sanitary landfill |  | 3000000
Procurement of Equipment for Sanitary landfill |  | 1200000
Relocation of Talipapa | Bantay Arcade | 483488.01
4683488.01
Environment and Infrastracture Development
Construction of residual containment area | Bantay Arcade | 200000
Concreting of Road with Protection works | Paing | 14000000 | Dec. 7, 2020 | June 5, 2021 | 99.9% | 13986006.5 |  | completed
Renovation of 2nd Floor RHU Building | RHU Building | 73373.34
|  | 14273373.34 |  |  |  | 13986006.5
We hereby certify that we have reviewed the contents and hereby attest to
the veracity and correctness of the data or information contained in this
document.
|  | FLORDELIZA P. REBOROSO |  |  |  | SAMUEL C. PARILLA
|  | Municipal Budget Officer |  |  |  | Municipal Mayor
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 4th QUARTER, CY 2019
Province, City / Municipality: Ilocos Sur/ Bantay
Program or | Location | Total Cost | Date Started | Target | Project Status |  | No. of
Project |  |  |  | Completion | % of | Total Cost Incurred | Extensions, if | Remarks
|  |  |  | Date | Completion | to Date | any
Social Development | Bantay, I. Sur
Rehabilitation & Maint. of Gov't. centers and facilities | -do- | 950000 | January | December | 96.27% | 914524 |  | completed
Rehabilitation & Maint. of Historical/Cultural sites | -do- | 600000 | January | December | 99.89% | 599315 |  | completed
Maintenance of Street lights | -do- | 751669 | January | December | 44.54% | 334760 |  | on going
|  | 2301669 |  |  |  | 1848599
Economic Development
Livestock Development (Provision for vaccines) | All barangays | 100000 | June | December | 100% | 98652 |  | completed
Livelihood projects (Livestock dispersal) | All farming barangays | 1500000 | June | December | 100% | 1484500 |  | completed
Promotion & Development of organic fertilizer | 3 Farming baranagays | 50000 | June | December |  | 0 |  | not yet started
Provision of skills training on farming and livestock raising | 9 Farming barangays | 50000 | June | December |  | 0 |  | not yet started
Enhancement of Agricultural Production | 9 Farming barangays | 100000 | June | December |  | 0 |  | not yet started
|  | 1800000 |  |  |  | 1583152
Environmental Management
Declogging of canals | Brgy. I- Brgy. VI | 909072.6 | April | December | 99.85% | 907700 |  | completed
Purchase of lot for Sanitary landfill |  | 3000000 | June | December |  | 0 |  | not yet implemented
Rechanelling of River | Bulag-Cabalabgan-Sinabaan | 2900000 | March 1, 2019 | May 27, 2019 | 100% | 2885506.53 |  | completed
Rechanelling of River | Tay-ac-Lingsat | 3000000 | -do- | May 30, 2019 | 100% | 2986167.44 |  | completed
Rechanelling of River | Tay-ac | 2300000 | -do- | May 9, 2019 | 100% | 2288393.79 |  | completed
Rechanelling of River | San Mariano | 1300000 | -do- | April 0, 2019 | 100% | 1290342.75 |  | completed
Rechanelling of River | Taleb | 3500000 | -do- | June 14, 2019 | 100% | 3486439.06 |  | completed
|  | 16909072.6 |  |  |  | 13844549.57
We hereby certify that we have reviewed the contents and hereby attest to
the veracity and correctness of the data or information contained in this
document.
FLORDELIZA P. REBOROSO | [5 empty] | SAMUEL C. PARILLA
Municipal Budget Officer | [5 empty] | Municipal Mayor