## FDP Form 7
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 3rd QUARTER, CY 2021
Province, City / Municipality: Ilocos Sur/ Bantay
Program or | Location | Total Cost | Date Started | Target | Project Status |  | No. of
Project |  |  |  | Completion | % of | Total Cost Incurred | Extensions, if | Remarks
|  |  |  | Date | Completion | to Date | any
I. Current Appropriation
Economic Development
Amortization of existing loans | Bantay, I. Sur | 8439866.52 | January | December | 74.95% | 6325510.69
|  | 8439866.52 |  |  |  | 6325510.69
Environment and Infrastracture Development
Desilting/Rechanelling of creek | Taleb | 4600000 | Aug. 6 | Oct. 4 | 100% | 2758097.48 |  | completed
Desilting/Rechanelling of creek | Sinabaan, Puspus, Aggay | 4400000 | Aug. 6 | Oct. 4 | 100% | 2638141.22 |  | completed
Desilting/Rechanelling of creek | Cabaroan | 1000000 | Aug. 6 | Oct. 4 | 100% | 997009.85 |  | completed
|  | 10000000 |  |  |  | 6393248.55
Social Development
Indigent Funeral Service Assistance | Municipal wide | 1000000
Food Assitance and Other Relief Goods | -do- | 5050000
Procurement of Personal Protective Equipment | -do- | 400000
Procurement of Disinfectants | -do- | 196836.48
6646836.48
II. Continuing Appropriation
Social Development
Construction of Public Restroom | Town Plaza | 800000
Installation of Streetlights | Poblacion Brgys | 1259406
Covid-related expenses |  | 581049.21 | January | December | 100% | 578078.64 |  | completed | i
|  | 2640455.21 |  |  |  | 578078.64
Economic Development
Livelihood Projects (Livestock Dispersal) |  | 1500000 | July | Dec
Livelihood Development (Vaccines) |  | 150000 | May | July |  | 148835 |  | completed
Promotion and Development of Organic Fertilizer |  | 150000 | July | Dec
Provision of skills traing on Farming & Livestock Raising |  | 150000 | July | Dec
Enhancement of Agricultural Production |  | 150000 | July | Dec
2100000
Environmental Management
Purchase of Lot for Sanitary landfill |  | 3000000
Procurement of Equipment for Sanitary landfill |  | 1200000
Relocation of Talipapa | Bantay Arcade | 483488.01
4683488.01
Environment and Infrastracture Development
Construction of residual containment area | Bantay Arcade | 200000
Concreting of Road with Protection works | Paing | 14000000 | Dec. 7, 2020 | June 5, 2021 | 99.9% | 13986006.5 |  | completed
Renovation of 2nd Floor RHU Building | RHU Building | 73373.34
|  | 14273373.34 |  |  |  | 13986006.5
We hereby certify that we have reviewed the contents and hereby attest to
the veracity and correctness of the data or information contained in this
document.
|  | FLORDELIZA P. REBOROSO |  |  |  | SAMUEL C. PARILLA
|  | Municipal Budget Officer |  |  |  | Municipal Mayor