## FDP Form 7
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 3rd QUARTER, CY 2022
Province, City / Municipality: Ilocos Sur/ Bantay
Program or | Location | Total Cost | Date Started | Target | Project Status |  | No. of
Project |  |  |  | Completion Date | % of Completion | Total Cost Incurred to Date | Extensions, if any | Remarks
I. Current Appropriation
Economic Development
Livestock Development |  | 100000 | June | December |  | 99695
Livelihood Project ( Livestock Dispersal) |  | 1800000 | July | December
Promotion & Development of organic fertilizer |  | 100000 | June | December
Provision of Skills training on farming & livestock raising |  | 100000 | June | December
Enhancement of agricultural production |  | 100000 | June | December
Amortization of loans |  | 3189292.88 | January | December | 75.52% | 2408524.49
Rehab program for ASF affected hog raisres |  | 1000000 | June | December
Purchase of Fishing gear/paraphernalias |  | 200000 | June | November
Fisheries production and distribution |  | 200000 | June | November
Installation of fence at Bantay arcade |  | 500000
|  | 7289292.88 | 0 | 0 |  | 2508219.49 | 0 | 0
Social Development
Rehab & Maint. Of Gov't. centers and facilities | Bantay, I. Sur | 1130016.52 | June | Decmber |  | 136228.23
Procurement of Personal Protective Equipment | Bantay, I. Sur | 1500000 | June | December |  | 130350
Purchase of Medicines | Bantay, I. Sur | 4000000 | January | December | 50.42% | 2016965
Installation of Streeetlights | Barangay I-VI | 16300000 | June | December
Distribution of Jetmatic pumps | Bantay, I. Sur | 1700000 | August | January
Repair & Maintenance of Streetlights | Bantay, I. Sur | 2000000 | June | December
|  | 26630016.52 |  |  |  | 2283543.23
II. Continuing Appropriation
Social Development
Rehab. & Maint. Of gov't. facilities |  | 73373.34
Construction of Public Restroom | Town Plaza | 800000
Installation of Streetlights | Poblacion Brgys | 1259406
Indigent Funeral Service Assistance |  | 924000
Food Assistance and Other Relief goods |  | 175000
Procurement of PPE |  | 158500
Procurement of Disinfectants |  | 38910.48
Covid-related expenses | Bantay, I. Sur | 2970.57 | [6 empty] | i
|  | 3432160.39 |  |  |  | 0
Economic Development
Loan Amortization- Interest |  | 66524.88
Livelihood Projects (Livestock Dispersal) | Bantay, I. Sur | 201400
Livelihood Development (Vaccines) | Bantay, I. Sur | 1165
Promotion and Development of Organic Fertilizer | Bantay, I. Sur | 150000
Provision of skills traing on Farming & Livestock Raising | Bantay, I. Sur | 150000
Enhancement of Agricultural Production | Bantay, I. Sur | 150000
|  | 719089.88 |  |  |  | 0
Environmental Management
Purchase of Lot for Sanitary landfill | Taleb | 3000000
Procurement of Equipment for Sanitary landfill | Taleb | 1200000
Relocation of Talipapa | Bantay Arcade | 483488.01
Construction of residual containment area | Bantay Arcade | 200000
Concreting of Road with Protection works | Paing | 13993.5
Desilting/Rechanelling of creek | Taleb | 3269.47
Desilting/Rechanelling of creek | Sinabaan-Puspus | 3453.43
Desilting/Rechanelling of creek | Cabaroan | 2990.15
|  | 4907194.56 |  |  |  | 0
We hereby certify that we have reviewed the contents and hereby attest to
the veracity and correctness of the data or information contained in this
document.
|  | FLORDELIZA P. REBOROSO |  |  |  | SAMUEL C. PARILLA
|  | Municipal Budget Officer |  |  |  | Municipal Mayor
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 4th QUARTER, CY 2019
Province, City / Municipality: Ilocos Sur/ Bantay
Program or | Location | Total Cost | Date Started | Target | Project Status |  | No. of
Project |  |  |  | Completion | % of | Total Cost Incurred | Extensions, if | Remarks
|  |  |  | Date | Completion | to Date | any
Social Development | Bantay, I. Sur
Rehabilitation & Maint. of Gov't. centers and facilities | -do- | 950000 | January | December | 96.27% | 914524 |  | completed
Rehabilitation & Maint. of Historical/Cultural sites | -do- | 600000 | January | December | 99.89% | 599315 |  | completed
Maintenance of Street lights | -do- | 751669 | January | December | 44.54% | 334760 |  | on going
|  | 2301669 |  |  |  | 1848599
Economic Development
Livestock Development (Provision for vaccines) | All barangays | 100000 | June | December | 100% | 98652 |  | completed
Livelihood projects (Livestock dispersal) | All farming barangays | 1500000 | June | December | 100% | 1484500 |  | completed
Promotion & Development of organic fertilizer | 3 Farming baranagays | 50000 | June | December |  | 0 |  | not yet started
Provision of skills training on farming and livestock raising | 9 Farming barangays | 50000 | June | December |  | 0 |  | not yet started
Enhancement of Agricultural Production | 9 Farming barangays | 100000 | June | December |  | 0 |  | not yet started
|  | 1800000 |  |  |  | 1583152
Environmental Management
Declogging of canals | Brgy. I- Brgy. VI | 909072.6 | April | December | 99.85% | 907700 |  | completed
Purchase of lot for Sanitary landfill |  | 3000000 | June | December |  | 0 |  | not yet implemented
Rechanelling of River | Bulag-Cabalabgan-Sinabaan | 2900000 | March 1, 2019 | May 27, 2019 | 100% | 2885506.53 |  | completed
Rechanelling of River | Tay-ac-Lingsat | 3000000 | -do- | May 30, 2019 | 100% | 2986167.44 |  | completed
Rechanelling of River | Tay-ac | 2300000 | -do- | May 9, 2019 | 100% | 2288393.79 |  | completed
Rechanelling of River | San Mariano | 1300000 | -do- | April 0, 2019 | 100% | 1290342.75 |  | completed
Rechanelling of River | Taleb | 3500000 | -do- | June 14, 2019 | 100% | 3486439.06 |  | completed
|  | 16909072.6 |  |  |  | 13844549.57
We hereby certify that we have reviewed the contents and hereby attest to
the veracity and correctness of the data or information contained in this
document.
FLORDELIZA P. REBOROSO | [5 empty] | SAMUEL C. PARILLA
Municipal Budget Officer | [5 empty] | Municipal Mayor