## spp 1st qtr
Municipality of Bantay
Barangay V, Bantay, Ilocos Sur
CY 2020 SUPPLEMENTAL PROCUREMENT PLAN - 1st QTR
CODE | PROGRAM/ACITIVITY/PROJECT | END USER | MODE OF PROCUREMENT |  | SCHEDULE FOR EACH PROCUREMENT ACTIVITY | [9 empty] | SOURCE OF FUNDS | Estimated Budget PhP |  |  | Remarks/Activity (Brief Description of Program/Project)
|  |  |  | PRE-PROC CONF | ADS/POST OF ITB | PRE-BID CONF | SUB/OPEN OF BIDS | BID EVALUATION | POST QUAL | NOTICE OF AWARD | CONTRACT SIGNING | NOTICE TO PROCEED | DELIVERY/ COMPLETION | ACCEPTANCE/TURNOVER |  | PS | MOOE | CO
| Repair/Maintenance of Comfort Room & Water System at San Julian Elementary School | LSB | Public Bidding | n/a | Feb. 25 | N/A | Mar.18 | Mar. 19 | Mar. 20 | Mar. 24 | Nov. 14 | Mar. 26 | Apr. 14 | Apr. 15 | SEF |  |  | 266871.42 | Building Repair and Water System
| Construction of School Stage at Bantay National High School | LSB | Public Bidding | n/a | Feb. 25 | N/A | Mar.18 | Mar. 19 | Mar. 20 | Mar. 24 | Nov. 14 | Mar. 26 | Apr. 29 | Apr. 30 | SEF |  |  | 532624.33 | Construction of Stage
| Construction of Drainage Canal at Tay-ac National High School | LSB | Public Bidding | n/a | Feb. 25 | N/A | Mar.18 | Mar. 19 | Mar. 20 | Mar. 24 | Nov. 14 | Mar. 26 | Apr. 14 | Apr. 15 | SEF |  |  | 293184.53 | Drainage Canal
| Purchase of Desktop Computer | LSB | Small Value Procurement | n/a | Feb. 25 | n/a | n/a | n/a | n/a | Mar. 3 | Mar. 4 | Mar. 5 | Mar. 6 | Mar. 6 | SEF |  |  | 60000 | Computer
| Purchase of three (3) Units Window Type Aircon | LSB | Small Value Procurement | n/a | Feb. 25 | n/a | n/a | n/a | n/a | Mar. 3 | Mar. 4 | Mar. 5 | Mar. 6 | Mar. 6 | SEF |  |  | 105000 | Aircon
Nothing follows
Prepared by BAC Secretariat:
WILLIAM V. PADRE
Recommending Approval:
| JONATHAN V. GOROSPE |  |  | LEONARDO L. PAET |  |  |  | JAY V. VILLAFRANCA |  |  |  | CONCEPCION J. MADRIAGA |  |  |  | FLORDELIZA P. REBOROSO
| BAC CHAIRMAN |  |  | BAC VICE CHAIRMAN |  |  |  | BAC MEMBER |  |  |  | BAC MEMBER |  |  |  | BAC MEMBER
Approved:
SAMUEL C. PARILLA
Municipal Mayor

## spp 2nd qtr
Municipality of Bantay
Barangay V, Bantay, Ilocos Sur
CY 2020 SUPPLEMENTAL PROCUREMENT PLAN - 2nd QTR
CODE | PROGRAM/ACITIVITY/PROJECT | END USER | MODE OF PROCUREMENT |  | SCHEDULE FOR EACH PROCUREMENT ACTIVITY | [9 empty] | SOURCE OF FUNDS | Estimated Budget PhP |  |  | Remarks/Activity (Brief Description of Program/Project)
|  |  |  | PRE-PROC CONF | ADS/POST OF ITB | PRE-BID CONF | SUB/OPEN OF BIDS | BID EVALUATION | POST QUAL | NOTICE OF AWARD | CONTRACT SIGNING | NOTICE TO PROCEED | DELIVERY/ COMPLETION | ACCEPTANCE/TURNOVER |  | PS | MOOE | CO
| Procurement of Personal Protective Equipment | LGU | Emergency Procurement per RA11469 | n/a | n/a | n/a | n/a | n/a | n/a | 2020-04-24 | 2020-04-27 | 2020-04-28 | 2020-04-29 | 2020-04-29 | Bayanihan Grant/Subsidy (BGCM) |  |  | 359000 | PPEs
| Procurement of Medicines and Vitamins | LGU | Emergency Procurement per RA11470 | n/a | n/a | n/a | n/a | n/a | n/a | 2020-04-24 | 2020-04-27 | 2020-04-28 | 2020-04-29 | 2020-04-29 | Bayanihan Grant/Subsidy (BGCM) |  |  | 275000 | Medicines and Vitamis
| Procurement of Disinfectants & other Disinfecting Supplies | LGU | Emergency Procurement per RA11471 | n/a | n/a | n/a | n/a | n/a | n/a | 2020-04-24 | 2020-04-27 | 2020-04-28 | 2020-04-29 | 2020-04-29 | Bayanihan Grant/Subsidy (BGCM) |  |  | 183000 | Disinfectants
| Procurement of Hospital Equipment and Supplies | LGU | Emergency Procurement per RA11472 | n/a | n/a | n/a | n/a | n/a | n/a | 2020-04-24 | 2020-04-27 | 2020-04-28 | 2020-04-29 | 2020-04-29 | Bayanihan Grant/Subsidy (BGCM) |  |  | 167000 | Hospital Equipment and Supplies
| Purchas eof Foods for Medical Personnel & other LGU Personnel | LGU | Emergency Procurement per RA11473 | n/a | n/a | n/a | n/a | n/a | n/a | 2020-04-24 | 2020-04-27 | 2020-04-28 | 2020-04-29 | 2020-04-29 | Bayanihan Grant/Subsidy (BGCM) |  |  | 732300 | Foods
| Food Assistance & Other Relief Goods | LGU | Emergency Procurement per RA11474 | n/a | n/a | n/a | n/a | n/a | n/a | 2020-04-24 | 2020-04-27 | 2020-04-28 | 2020-04-29 | 2020-04-29 | Bayanihan Grant/Subsidy (BGCM) |  |  | 8036554 | Rice and Goods
Nothing follows
Prepared by BAC Secretariat:
WILLIAM V. PADRE
Recommending Approval:
| JONATHAN V. GOROSPE |  |  | LEONARDO L. PAET |  |  |  | JAY V. VILLAFRANCA |  |  |  | CONCEPCION J. MADRIAGA |  |  |  | FLORDELIZA P. REBOROSO
| BAC CHAIRMAN |  |  | BAC VICE CHAIRMAN |  |  |  | BAC MEMBER |  |  |  | BAC MEMBER |  |  |  | BAC MEMBER
Approved:
SAMUEL C. PARILLA
Municipal Mayor

## spp 2nd qtr-a
Municipality of Bantay
Barangay V, Bantay, Ilocos Sur
CY 2020 SUPPLEMENTAL PROCUREMENT PLAN - 2nd QTR-A
CODE | PROGRAM/ACITIVITY/PROJECT | END USER | MODE OF PROCUREMENT |  | SCHEDULE FOR EACH PROCUREMENT ACTIVITY | [9 empty] | SOURCE OF FUNDS | Estimated Budget PhP |  |  | Remarks/Activity (Brief Description of Program/Project)
|  |  |  | PRE-PROC CONF | ADS/POST OF ITB | PRE-BID CONF | SUB/OPEN OF BIDS | BID EVALUATION | POST QUAL | NOTICE OF AWARD | CONTRACT SIGNING | NOTICE TO PROCEED | DELIVERY/ COMPLETION | ACCEPTANCE/TURNOVER |  | PS | MOOE | CO
| Purchase of Furniture & Fixtures | SB Office | Small Value Procurement | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | General Fund |  |  | 50000
| Purchase of Furniture & Fixtures | MPDC | Small Value Procurement | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | General Fund |  |  | 60000
| Purchase of Furniture & Fixtures | Accounting Office | Small Value Procurement | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | General Fund |  |  | 60000
| Purchase of Furniture & Fixtures | Treasury | Small Value Procurement | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | General Fund |  |  | 100000
| Purchase of Furniture & Fixtures | Engineering Office | Small Value Procurement | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | General Fund |  |  | 30000
| Improvement of RHU Building | LGU Bantay | Public Bidding | n/a | 2020-05-08 | 2020-05-15 | 2020-05-27 | 2020-05-28 | 2020-05-29 | 2020-06-02 | 2020-06-02 | 2020-06-04 | 2020-06-18 | 2020-06-19 | General Fund |  |  | 500000
| Construction of Flood Control at Tay-ac | LGU Bantay | Public Bidding | n/a | 2020-05-08 | 2020-05-15 | 2020-05-27 | 2020-05-28 | 2020-05-29 | 2020-06-02 | 2020-06-02 | 2020-06-04 | 2020-08-02 | 2020-08-03 | General Fund |  |  | 3734033.95
| Construction of Flood Control at An-annam | LGU Bantay | Public Bidding | n/a | 2020-05-08 | 2020-05-15 | 2020-05-27 | 2020-05-28 | 2020-05-29 | 2020-06-02 | 2020-06-02 | 2020-06-04 | 2020-08-02 | 2020-08-03 | General Fund |  |  | 3617267.94
| Purchase of Furniture & Fixtures | Administrator Office | Small Value Procurement | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | General Fund |  |  | 40000
| Purchase of Furniture & Fixtures | Agriculture Office | Small Value Procurement | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | General Fund |  |  | 60000
| Purchase of Furniture & Fixtures | MSWDO | Small Value Procurement | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | General Fund |  |  | 50000
| Purchase of Furniture & Fixtures | MHO | Small Value Procurement | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | General Fund |  |  | 150000
| Purchase of I.T. Equipment | Budget Office | Small Value Procurement | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | General Fund |  |  | 80000
| Purchase of I.T. Equipment | Accounting Office | Small Value Procurement | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | General Fund |  |  | 80000
| Purchase of I.T. Equipment | Treasury | Small Value Procurement | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | General Fund |  |  | 50000
| Purchase of I.T. Equipment | Administrator Office | Small Value Procurement | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | General Fund |  |  | 50000
| Purchase of I.T. Equipment | Agriculture Office | Small Value Procurement | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | General Fund |  |  | 70000
page 1 of 2
| Purchase of I.T. Equipment | MSWDO | Small Value Procurement | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | General Fund |  |  | 20000
| Purchase of I.T. Equipment | MHO | Small Value Procurement | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | General Fund |  |  | 150000
| Purchase of I.T. Equipment | MDRRMO | Small Value Procurement | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | General Fund |  |  | 50000
| Purchase of Furniture & Fixtures (Office Table and Chair) | MDRRMO | Small Value Procurement | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | General Fund |  |  | 9000
| Purchase of DRRM Tools and Equipment | MDRRMO | Public Bidding | 2020-05-08 | 2020-05-15 | 2020-05-27 | 2020-05-28 | 2020-05-29 | 2020-06-02 | 2020-06-02 | 2020-06-04 | 2020-06-11 | 2020-06-11 | 2020-06-12 | General Fund |  |  | 341851.5
| Purchase of I.T. Equipment | MBPLO | Small Value Procurement | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | General Fund |  |  | 50000
| Purchase of Office Equipment/OPPE | Administrator Office | Small Value Procurement | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | General Fund |  |  | 30000
| Purchase of Office Equipment/OPPE (1 1/2 fire fighting hose for water system) | Operation of Arcade | Small Value Procurement | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | General Fund |  |  | 70000
| Purchase of ambulance | LGU Bantay | Public Bidding | 2020-05-08 | 2020-05-15 | 2020-05-27 | 2020-05-28 | 2020-05-29 | 2020-06-02 | 2020-06-02 | 2020-06-04 | 2020-06-11 | 2020-06-11 | 2020-06-12 | General Fund |  |  | 860000
| Purchase of three (3) Units Multi-Purpose Vehicle | LGU Bantay | Public Bidding | 2020-05-08 | 2020-05-15 | 2020-05-27 | 2020-05-28 | 2020-05-29 | 2020-06-02 | 2020-06-02 | 2020-06-04 | 2020-06-11 | 2020-06-11 | 2020-06-12 | General Fund & DILG-PCF |  |  | 3045000
Nothing Follows
Prepared by BAC Secretariat:
WILLIAM V. PADRE
Recommending Approval:
| JONATHAN V. GOROSPE |  |  | 2020-05-08: LEONARDO L. PAET; 2020-05-29: JAY V. VILLAFRANCA; 2020-06-11: CONCEPCION J. MADRIAGA |  | FLORDELIZA P. REBOROSO
| BAC CHAIRMAN |  |  | 2020-05-08: BAC VICE CHAIRMAN; 2020-05-29: BAC MEMBER; 2020-06-11: BAC MEMBER |  | BAC MEMBER
Approved:
SAMUEL C. PARILLA
Municipal Mayor
page 2 of 2

## spp 2nd qtr-b
Municipality of Bantay
Barangay V, Bantay, Ilocos Sur
CY 2020 SUPPLEMENTAL PROCUREMENT PLAN - 2nd QTR-B
CODE | PROGRAM/ACITIVITY/PROJECT | END USER | MODE OF PROCUREMENT |  | SCHEDULE FOR EACH PROCUREMENT ACTIVITY | [9 empty] | SOURCE OF FUNDS | Estimated Budget PhP |  |  | Remarks/Activity (Brief Description of Program/Project)
|  |  |  | PRE-PROC CONF | ADS/POST OF ITB | PRE-BID CONF | SUB/OPEN OF BIDS | BID EVALUATION | POST QUAL | NOTICE OF AWARD | CONTRACT SIGNING | NOTICE TO PROCEED | DELIVERY/ COMPLETION | ACCEPTANCE/TURNOVER |  | PS | MOOE | CO
| Purchase of 1 Unit Laptop | PNP Bantay | Small Value Procurement | n/a | 2015-07-01 | n/a | n/a | n/a | n/a | Jul. 21 | n/a | n/a | n/a | n/a | Trust Fund |  |  | 70000
| Purchase of 2 Units Patrol Motorcycle with Accessories | PNP Bantay | Public Bidding | n/a | 2015-07-01 | 2023-07-01 | Aug. 5 | Aug. 6 | Aug. 7 | Aug. 12 | Aug. 13 | Aug. 14 | Sep. 14 | Sep. 14 | DILG-PCF |  |  | 270000
Nothing Follows
Prepared by BAC Secretariat:
WILLIAM V. PADRE
Recommending Approval:
| JONATHAN V. GOROSPE |  |  | LEONARDO L. PAET |  |  |  | JAY V. VILLAFRANCA |  |  |  | CONCEPCION J. MADRIAGA |  |  |  | FLORDELIZA P. REBOROSO
| BAC CHAIRMAN |  |  | BAC VICE CHAIRMAN |  |  |  | BAC MEMBER |  |  |  | BAC MEMBER |  |  |  | BAC MEMBER
Approved:
SAMUEL C. PARILLA
Municipal Mayor
page 1 of 1

## spp 3rd qtr
Municipality of Bantay
Barangay V, Bantay, Ilocos Sur
CY 2020 SUPPLEMENTAL PROCUREMENT PLAN - 3rd QTR
CODE | PROGRAM/ACITIVITY/PROJECT | END USER | MODE OF PROCUREMENT |  | SCHEDULE FOR EACH PROCUREMENT ACTIVITY | [9 empty] | SOURCE OF FUNDS | Estimated Budget PhP |  |  | Remarks/Activity (Brief Description of Program/Project)
|  |  |  | PRE-PROC CONF | ADS/POST OF ITB | PRE-BID CONF | SUB/OPEN OF BIDS | BID EVALUATION | POST QUAL | NOTICE OF AWARD | CONTRACT SIGNING | NOTICE TO PROCEED | DELIVERY/ COMPLETION | ACCEPTANCE/TURNOVER |  | PS | MOOE | CO
| Rehabilitation of Comfort Room @ 2nd Floor RHU Bldg., Brgy. V, Bantay, Ilocos Sur | LGU Bantay | Public Bidding | n/a | July 27, 2020 | n/a | August 24, 2020 | August 25, 2020 | august 26, 2020 | Jul. 21 | August 24, 2020 | August 26, 2020 | Ocotber 9, 2020 | October 12, 2020 | 20% ADP |  |  | 793752.42 | Confort Room
| Improvement of Mayor's Office Extension | LGU Bantay | Public Bidding | n/a | July 27, 2021 | n/a | August 24, 2021 | August 25, 2021 | august 26, 2021 | Jul. 22 | August 24, 2021 | August 26, 2021 | September 30, 2020 | October 1, 2021 | General Fund |  |  | 744112.6 | Office Improvement
| Purchase and Installation of 3 Units Cabinet Type Aircon; 1 Unit Split Type Aircon 2.5 HP; and 1 Unit Window Tyope Aircon 2 HP | RHU | Public Bidding | n/a | July 27, 2022 | n/a | August 24, 2022 | August 25, 2022 | august 26, 2022 | Jul. 23 | August 24, 2022 | August 26, 2022 | September 1, 2022 | September 2, 2020 | General Fund |  |  | 465500 | Aircon
| Purchase of Athletic Uniform for Unit II Meet | DepEd Bantay | Small Value Procurement | n/a | July 27, 2020 | n/a | n/a | n/a | n/a | July 31, 2020 | n/a | n/a | n/a | n/a | SEF |  |  | 81792 | Uniform
| Purchase of Traffic Uniform & Equipment | LGU Bantay | Small Value Procurement | n/a | July 27, 2020 | n/a | n/a | n/a | n/a | July 31, 2021 | n/a | n/a | n/a | n/a | Trust Fund |  |  | 57600 | Uniform & Equipment
| Purchase of 1 Unit split Type Inverter Aircon 2.5 HP | MPDC | Small Value Procurement | n/a | July 27, 2020 | n/a | n/a | n/a | n/a | July 31, 2022 | n/a | n/a | n/a | n/a | General Fund |  |  | 60000 | Aircon
Nothing Follows
Prepared by BAC Secretariat:
WILLIAM V. PADRE
Recommending Approval:
| JONATHAN V. GOROSPE |  |  | LEONARDO L. PAET |  |  |  | JAY V. VILLAFRANCA |  |  |  | CONCEPCION J. MADRIAGA |  |  |  | FLORDELIZA P. REBOROSO
| BAC CHAIRMAN |  |  | BAC VICE CHAIRMAN |  |  |  | BAC MEMBER |  |  |  | BAC MEMBER |  |  |  | BAC MEMBER
Approved:
SAMUEL C. PARILLA
Municipal Mayor
page 1 of 1

## spp 3rd qtr-A
Municipality of Bantay
Barangay V, Bantay, Ilocos Sur
CY 2020 SUPPLEMENTAL PROCUREMENT PLAN - 3rd QTR-A
CODE | PROGRAM/ACITIVITY/PROJECT | END USER | MODE OF PROCUREMENT |  | SCHEDULE FOR EACH PROCUREMENT ACTIVITY | [9 empty] | SOURCE OF FUNDS | Estimated Budget PhP |  |  | Remarks/Activity (Brief Description of Program/Project)
|  |  |  | PRE-PROC CONF | ADS/POST OF ITB | PRE-BID CONF | SUB/OPEN OF BIDS | BID EVALUATION | POST QUAL | NOTICE OF AWARD | CONTRACT SIGNING | NOTICE TO PROCEED | DELIVERY/ COMPLETION | ACCEPTANCE/TURNOVER |  | PS | MOOE | CO
| Food Expense | LGU Bantay | Emergency Cases (GPPB Res. 03-2020 Dated March 9, 2020 | n/a | August 13, 2020 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | As need arises | n/a | 20% ADP |  |  | 900000 | Covid Related Activities
| Covid related Expense | LGU Bantay | Emergency Cases (GPPB Res. 03-2020 Dated March 9, 2020 | n/a | August 13, 2021 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | As need arises | n/a | 20% ADP |  |  | 754190.6 | Covid Related Activities
Nothing Follows
Prepared by BAC Secretariat:
WILLIAM V. PADRE
Recommending Approval:
| JONATHAN V. GOROSPE |  |  | LEONARDO L. PAET |  |  |  | JAY V. VILLAFRANCA |  |  |  | CONCEPCION J. MADRIAGA |  |  |  | FLORDELIZA P. REBOROSO
| BAC CHAIRMAN |  |  | BAC VICE CHAIRMAN |  |  |  | BAC MEMBER |  |  |  | BAC MEMBER |  |  |  | BAC MEMBER
Approved:
SAMUEL C. PARILLA
Municipal Mayor
page 1 of 1

## spp 3rd-B
Municipality of Bantay
Barangay V, Bantay, Ilocos Sur
CY 2020 SUPPLEMENTAL PROCUREMENT PLAN - 3rd QTR-B
CODE | PROGRAM/ACITIVITY/PROJECT | END USER | MODE OF PROCUREMENT |  | SCHEDULE FOR EACH PROCUREMENT ACTIVITY | [9 empty] | SOURCE OF FUNDS | Estimated Budget PhP |  |  | Remarks/Activity (Brief Description of Program/Project)
|  |  |  | PRE-PROC CONF | ADS/POST OF ITB | PRE-BID CONF | SUB/OPEN OF BIDS | BID EVALUATION | POST QUAL | NOTICE OF AWARD | CONTRACT SIGNING | NOTICE TO PROCEED | DELIVERY/ COMPLETION | ACCEPTANCE/TURNOVER |  | PS | MOOE | CO
| Purchase of Three (3) Units Xerox Machine for BNHS, TNHS & DepEd Bantay Dist. | Local School Board | Public Bidding | n/a | Aug. 31 | n/a | n/a | n/a | n/a | Sept. 10 | n/a | n/a | n/a | n/a | SEF |  |  | 270000 | Copier Machine
| Purchase of Eighteen Units Printer for DepEd Bantay District (Different Elementary Schools) | Local School Board | Small Value Procurement | n/a | Aug. 31 | n/a | n/a | n/a | n/a | Sept. 10 | n/a | n/a | n/a | n/a | SEF |  |  | 150000 | Printer for different elementary schools
| Purchase of One (1) Unit Desktop with Printer for DepEd Bantay Dist. Office | Local School Board | Small Value Procurement | n/a | Aug. 31 | n/a | n/a | n/a | n/a | Sept. 10 | n/a | n/a | n/a | n/a | SEF |  |  | 60000 | Computer for Dist. Office
| Repair and Rehabilitation of Two (2) Classroom , Comfort Rooms and Water System at San Julian Elem. School | Local School Board | Public Bidding | n/a | Aug. 27 | n/a | Sept. 21 | Sept. 22 | Sept. 23 | Sept. 28 | Sept. 29 | Sept. 30 | Oct. 15 | Oct. 16 | SEF |  |  | 267209.92 | Repair and Maintenance
| Construction of Drainage Canal at Tay-ac National High School | Local School Board | Public Bidding | n/a | Aug. 27 | n/a | Sept. 21 | Sept. 22 | Sept. 23 | Sept. 28 | Sept. 29 | Sept. 30 | Oct. 15 | Oct. 16 | SEF |  |  | 294000 | Drainage Canal
| Constrction of School Stage at Bantay National High School | Local School Board | Public Bidding | n/a | Aug. 27 | n/a | Sept. 21 | Sept. 22 | Sept. 23 | Sept. 28 | Sept. 29 | Sept. 30 | Oct. 29 | Oct. 30 | SEF |  |  | 533000 | School Stage
Nothing Follows
Prepared by BAC Secretariat:
WILLIAM V. PADRE
Recommending Approval:
| JONATHAN V. GOROSPE |  |  | LEONARDO L. PAET |  |  |  | JAY V. VILLAFRANCA |  |  |  | CONCEPCION J. MADRIAGA |  |  |  | FLORDELIZA P. REBOROSO
| BAC CHAIRMAN |  |  | BAC VICE CHAIRMAN |  |  |  | BAC MEMBER |  |  |  | BAC MEMBER |  |  |  | BAC MEMBER
Approved:
SAMUEL C. PARILLA
Municipal Mayor
page 1 of 1

## spp 3rd qtr-C
Municipality of Bantay
Barangay V, Bantay, Ilocos Sur
CY 2020 SUPPLEMENTAL PROCUREMENT PLAN - 3rd QTR-C
CODE | PROGRAM/ACITIVITY/PROJECT | END USER | MODE OF PROCUREMENT |  | SCHEDULE FOR EACH PROCUREMENT ACTIVITY | [9 empty] | SOURCE OF FUNDS | Estimated Budget PhP |  |  | Remarks/Activity (Brief Description of Program/Project)
|  |  |  | PRE-PROC CONF | ADS/POST OF ITB | PRE-BID CONF | SUB/OPEN OF BIDS | BID EVALUATION | POST QUAL | NOTICE OF AWARD | CONTRACT SIGNING | NOTICE TO PROCEED | DELIVERY/ COMPLETION | ACCEPTANCE/TURNOVER |  | PS | MOOE | CO
| Rehabilitation of Sitio Pinto-Portugues Road at Tay-ac | LGU Bantay | Public Bidding | n/a | Sept. 1 | Sept. 10 | Sept. 23 | Sept. 24 | Sept. 28 | Sept. 29 | Sept. 29 | Oct. 1 | Nove. 6 | Nov. 9 | DILG-AM |  |  | 3992908.31 | Infrastructure
| Rehabilitation of Sitio Riverside Road at An-annam | LGU Bantay | Public Bidding | n/a | Sept. 1 | Sept. 10 | Sept. 23 | Sept. 24 | Sept. 28 | Sept. 29 | Sept. 29 | Oct. 1 | Nove. 15 | Nov. 16 | DILG-AM |  |  | 3276275.07 | Infrastructure
| Rehabilitation of Barangay Sagpat Road | LGU Bantay | Public Bidding | n/a | Sept. 1 | Sept. 10 | Sept. 23 | Sept. 24 | Sept. 28 | Sept. 29 | Sept. 29 | Oct. 1 | Nove. 15 | Nov. 16 | DILG-AM |  |  | 4348366.81 | Infrastructure
Nothing Follows
Prepared by BAC Secretariat:
WILLIAM V. PADRE
Recommending Approval:
| JONATHAN V. GOROSPE |  |  | LEONARDO L. PAET |  |  |  | JAY V. VILLAFRANCA |  |  |  | CONCEPCION J. MADRIAGA |  |  |  | FLORDELIZA P. REBOROSO
| BAC CHAIRMAN |  |  | BAC VICE CHAIRMAN |  |  |  | BAC MEMBER |  |  |  | BAC MEMBER |  |  |  | BAC MEMBER
Approved:
SAMUEL C. PARILLA
Municipal Mayor
page 1 of 1

## spp 4th qtr
Municipality of Bantay
Barangay V, Bantay, Ilocos Sur
CY 2020 SUPPLEMENTAL PROCUREMENT PLAN - 4th QTR
CODE | PROGRAM/ACITIVITY/PROJECT | END USER | MODE OF PROCUREMENT |  | SCHEDULE FOR EACH PROCUREMENT ACTIVITY | [9 empty] | SOURCE OF FUNDS | Estimated Budget PhP |  |  | Remarks/Activity (Brief Description of Program/Project)
|  |  |  | PRE-PROC CONF | ADS/POST OF ITB | PRE-BID CONF | SUB/OPEN OF BIDS | BID EVALUATION | POST QUAL | NOTICE OF AWARD | CONTRACT SIGNING | NOTICE TO PROCEED | DELIVERY/ COMPLETION | ACCEPTANCE/TURNOVER |  | PS | MOOE | CO
| Purchase of 79 Pieces Toilet Bowls and 79 Bags Cement | MHO | Small Value Procurement | n/a | Nov. 9, 2020 | n/a | n/a | n/a | n/a | Nov. 12, 2020 | n/a | n/a | n/a | n/a | General Fund |  | 80000 |  | Health and Sanitation
| Concreting of Road with Protection works at Paing, Bantay, Ilocos Sur | LGU Bantay | Public Bidding | Nov. 4, 2020 | Nov. 9, 2020 | Nov. 17, 2020 | Dec. 1, 2020 | Dec. 2, 2020 | Dec. 4, 2020 | Dec. 8, 2020 | Dec. 8, 2020 | Dec. 10, 2020 | Jul. 10, 2021 | Jul. 12, 2021 | 20% ADP |  |  | 13987261.02 | Infrastructure
| Installation of Closed Circuit Television (CCTV) along the MNR from Buquig to Balaleng | LGU Bantay | Public Bidding | Nov. 4, 2020 | Nov. 9, 2020 | Nov. 17, 2020 | Dec. 1, 2020 | Dec. 2, 2020 | Dec. 4, 2020 | Dec. 8, 2020 | Dec. 8, 2020 | Dec. 10, 2020 | Jan. 11, 2021 | Jan. 12, 2021 | General Fund |  |  | 2300000 | CCTV
Nothing Follows
Prepared by BAC Secretariat:
WILLIAM V. PADRE
Recommending Approval:
| JONATHAN V. GOROSPE |  |  | LEONARDO L. PAET |  |  |  | JAY V. VILLAFRANCA |  |  |  | CONCEPCION J. MADRIAGA |  |  |  | FLORDELIZA P. REBOROSO
| BAC CHAIRMAN |  |  | BAC VICE CHAIRMAN |  |  |  | BAC MEMBER |  |  |  | BAC MEMBER |  |  |  | BAC MEMBER
Approved:
SAMUEL C. PARILLA
Municipal Mayor
page 1 of 1

## spp 4th qtr-a
Municipality of Bantay
Barangay V, Bantay, Ilocos Sur
CY 2020 SUPPLEMENTAL PROCUREMENT PLAN - 4th QTR-A
CODE | PROGRAM/ACITIVITY/PROJECT | END USER | MODE OF PROCUREMENT |  | SCHEDULE FOR EACH PROCUREMENT ACTIVITY | [9 empty] | SOURCE OF FUNDS | Estimated Budget PhP |  |  | Remarks/Activity (Brief Description of Program/Project)
|  |  |  | PRE-PROC CONF | ADS/POST OF ITB | PRE-BID CONF | SUB/OPEN OF BIDS | BID EVALUATION | POST QUAL | NOTICE OF AWARD | CONTRACT SIGNING | NOTICE TO PROCEED | DELIVERY/ COMPLETION | ACCEPTANCE/TURNOVER |  | PS | MOOE | CO
| Purchase of 8 Units Aircons of Different Offices | MHO, MPDC, OM, MDRRMC | Public Bidding | n/a | Nov. 11, 2020 | n/a | Dec. 1, 2020 | Dec. 2, 2020 | Dec. 3, 2020 | Dec. 7, 2020 | Dec. 8, 2020 | Dec. 9, 2020 | Dec. 16, 2020 | Dec. 16, 2020 | General Fund |  | 580000 |  | Aircon
Nothing Follows
Prepared by BAC Secretariat:
WILLIAM V. PADRE
Recommending Approval:
| JONATHAN V. GOROSPE |  |  | LEONARDO L. PAET |  |  |  | JAY V. VILLAFRANCA |  |  |  | CONCEPCION J. MADRIAGA |  |  |  | FLORDELIZA P. REBOROSO
| BAC CHAIRMAN |  |  | BAC VICE CHAIRMAN |  |  |  | BAC MEMBER |  |  |  | BAC MEMBER |  |  |  | BAC MEMBER
Approved:
SAMUEL C. PARILLA
Municipal Mayor

## spp 4th qtr-b
Municipality of Bantay
Barangay V, Bantay, Ilocos Sur
CY 2020 SUPPLEMENTAL PROCUREMENT PLAN - 4th QTR-B
CODE | PROGRAM/ACITIVITY/PROJECT | END USER | MODE OF PROCUREMENT |  | SCHEDULE FOR EACH PROCUREMENT ACTIVITY | [9 empty] | SOURCE OF FUNDS | Estimated Budget PhP |  |  | Remarks/Activity (Brief Description of Program/Project)
|  |  |  | PRE-PROC CONF | ADS/POST OF ITB | PRE-BID CONF | SUB/OPEN OF BIDS | BID EVALUATION | POST QUAL | NOTICE OF AWARD | CONTRACT SIGNING | NOTICE TO PROCEED | DELIVERY/ COMPLETION | ACCEPTANCE/TURNOVER |  | PS | MOOE | CO
| Purchase of Christmas Décor | LGU Bantay | Small Value Procurement | n/a | Nov. 20, 2020 | n/a | n/a | n/a | n/a | Nov. 25, 2020 | n/a | n/a | n/a | n/a | General Fund |  | 100000 |  | Christmas Decorations
| Purchase of Fogging Reagents | RHU | Public Bidding | n/a | Nov. 20, 2020 | n/a | Dec. 10, 2020 | Dec. 11, 2020 | Dec. 14, 2020 | Dec. 16, 2020 | Dec. 16, 2020 | Dec. 18, 2020 | Dec. 23, 2020 | Dec. 23, 2020 | 5% Calamity Fund |  | 445500 |  | Fogging Reagents
| Water Sampling/Testing | RHU | Small Value Procurement | n/a | Nov. 20, 2020 | n/a | n/a | n/a | n/a | Nov. 25, 2020 | n/a | n/a | n/a | n/a | General Fund |  | 180000 |  | Water Sampling/Testing
Nothing Follows
Prepared by BAC Secretariat:
WILLIAM V. PADRE
Recommending Approval:
| JONATHAN V. GOROSPE |  |  | LEONARDO L. PAET |  |  |  | JAY V. VILLAFRANCA |  |  |  | CONCEPCION J. MADRIAGA |  |  |  | FLORDELIZA P. REBOROSO
| BAC CHAIRMAN |  |  | BAC VICE CHAIRMAN |  |  |  | BAC MEMBER |  |  |  | BAC MEMBER |  |  |  | BAC MEMBER
Approved:
SAMUEL C. PARILLA
Municipal Mayor

## spp 4th qtr-c
Municipality of Bantay
Barangay V, Bantay, Ilocos Sur
CY 2020 SUPPLEMENTAL PROCUREMENT PLAN - 4th QTR-C
CODE | PROGRAM/ ACTIVITY/PROJECT | END USER | MODE OF PROCUREMENT |  | SCHEDULE FOR EACH PROCUREMENT ACTIVITY | [9 empty] | SOURCE OF FUNDS | Estimated Budget PhP |  |  | Remarks/Activity (Brief Description of Program/Project)
|  |  |  | PRE-PROC CONF | ADS/POST OF ITB | PRE-BID CONF | SUB/OPEN OF BIDS | BID EVALUATION | POST QUAL | NOTICE OF AWARD | CONTRACT SIGNING | NOTICE TO PROCEED | DELIVERY/ COMPLETION | ACCEPTANCE/TURNOVER |  | PS | MOOE | CO
| Purchase of Rapid Antigen Test Kit | RHU | Small Value Procurement | n/a | Nov. 26, 2020 | n/a | n/a | n/a | n/a | Dec. 3, 2020 | n/a | n/a | n/a | n/a | General Fund |  | 138600 |  | Covid-19 Test Kit
Nothing Follows
Prepared by BAC Secretariat:
WILLIAM V. PADRE
Recommending Approval:
| JONATHAN V. GOROSPE |  |  | LEONARDO L. PAET |  |  |  | JAY V. VILLAFRANCA |  |  |  | CONCEPCION J. MADRIAGA |  |  |  | FLORDELIZA P. REBOROSO
| BAC CHAIRMAN |  |  | BAC VICE CHAIRMAN |  |  |  | BAC MEMBER |  |  |  | BAC MEMBER |  |  |  | BAC MEMBER
Approved:
SAMUEL C. PARILLA
Municipal Mayor